## Jira (1)
Issue Type | Issue key | Sprint | Summary | Assignee | Reporter | Reporter Id | Priority | Status | Issue id
Story | AL4-38 | Sprint 1 | As a user I need a registration page to create and account | Allen Zhang | Allen Zhang | 60bd76722bd214006921e72e | Medium | In Progress | 10037
Story | AL4-35 | Sprint 1 | As a user, I want a home and maps page so I can easily navigate the website | Justin Lee | Justin Lee | 60bfc509b215610069dbadcb | Medium | In Progress | 10034
Story | AL4-14 | Sprint 1 | As a user I want to find rock climbing and hiking locations | Erica Shivers | Erica Shivers | 60bd408918e9f60071b8962f | Medium | In Progress | 10013
Story | AL4-7 | Sprint 1 | As a user I want to input locations and dates so I can search for rides | Daniel Lisle | Allen Zhang | 60bd76722bd214006921e72e | Medium | In Progress | 10006
Story | AL4-5 | Sprint 1 | As a user I want to be able to chat with other users | Caleb Noel | Caleb Noel | 60b941b899418500746453e5 | Medium | In Progress | 10004
Story | AL4-27 | Sprint 2 | As a user, I want to be able to favorite locations that I most enjoy. | Erica Shivers | Justin Lee | 60bfc509b215610069dbadcb | Medium | Backlog | 10026
Story | AL4-24 | Sprint 2 | As a user, I want to see information about travelers similar to me so I can choose a ride | Daniel Lisle | Daniel Lisle | 60b940ee367bda00719945d7 | Medium | To Do | 10023
Story | AL4-22 | Sprint 2 | As an user, I should be able to rate the driver or rider | Allen Zhang | Allen Zhang | 60bd76722bd214006921e72e | Medium | To Do | 10021
Story | AL4-6 | Sprint 2 | As a driver I want post my destination and costs | Justin Lee | Allen Zhang | 60bd76722bd214006921e72e | Medium | To Do | 10005
Story | AL4-3 | Sprint 2 | As a user I want to find a ride to [destination] | Caleb Noel | Caleb Noel | 60b941b899418500746453e5 | Medium | Backlog | 10002
Story | AL4-33 | Sprint 3 | As a user I want to be able to edit my profile and add information about myself | Caleb Noel | Caleb Noel | 60b941b899418500746453e5 | Medium | Backlog | 10032
Story | AL4-26 | Sprint 3 | As a user, I want to add attributes about myself so I can interact with others most similar to me. | Justin Lee | Justin Lee | 60bfc509b215610069dbadcb | Medium | Backlog | 10025
Story | AL4-10 | Sprint 3 | As a user, I want to navigate to the registration page so I can start entering my info | Daniel Lisle | Daniel Lisle | 60b940ee367bda00719945d7 | Medium | Backlog | 10009
Story | AL4-9 | Sprint 3 | As a user I want to browse possible destinations or interesting locations on the map | Caleb Noel | Caleb Noel | 60b941b899418500746453e5 | Medium | To Do | 10008
Story | AL4-37 | Sprint 4 | As a user I want to view all my messages | Caleb Noel | Caleb Noel | 60b941b899418500746453e5 | Medium | Backlog | 10036
Story | AL4-36 | Sprint 4 | As a user I want to be able to search for users to chat | Caleb Noel | Caleb Noel | 60b941b899418500746453e5 | Medium | Backlog | 10035
Story | AL4-8 | Sprint 4 | As a user I want to add fun spots on the map or view existing spots | Allen Zhang | Allen Zhang | 60bd76722bd214006921e72e | Medium | To Do | 10007